## Risk Register
Risk Title | Risk ID | Project Name | Project ID | Budget Code | WO Number | PM Name | Submission Date | Project Budget ($k) | Project Duration (Weeks) | Record Version | Risk Description | Cause(s) | Effect(s) | RBS Category | Financial Flag | Risk Owner Group | Risk Owner Person | Risk Status | Source | Library Risk ID | Current Probability | Quantitative Estimates Available | Cost Min ($k) | Cost Most Likely ($k) | Cost Max ($k) | Schedule Impact Min (weeks) | Schedule Impact Most Likely (weeks) | Schedule Impact Max (weeks) | Cost Impact Qualitative | Schedule Impact Qualitative | Response Strategy | Action Plan | Action Owner | Action Review Date | Mitigation Cost | Has Risk Actualized | Date Actualized | Actualized Cost Impact ($k) | Actualized Schedule Impact (weeks) | Variance Explaination | Residual Probability | Residual Quantitative Estimates Available | Residual Cost Min ($k) | Residual Cost Most Likely ($k) | Residual Cost Max ($k) | Residual Schedule Min (weeks) | Residual Schedule Most Likely (weeks) | Residual Schedule Max (weeks) | Action Owner Group | Residual Cost Impact Qualitative | Residual Schedule Impact Qualitative | ID
Major Equipment Delivery Delay (Transformers, Switchgear) | 2021-2065-R-001 | URBAN SUBSTATION REBUILD | 2021-2065 | 19252 |  | Renger, Andy | 2026-03-10 | 11750 | 477 | 1 | Long-lead equipment not delivered within the schedule window required for construction sequencing. |  |  | Resources (People and Materials) | True |  | Renger, Andy | Active - Monitoring | Library | RS-002 | 3 | False | [13 empty] | False | [15 empty] | 3
Outage Constraints and Energized Equipment Work | 2021-2065-R-002 | URBAN SUBSTATION REBUILD | 2021-2065 | 19252 |  | Renger, Andy | 2026-03-10 | 11750 | 477 | 1 | Work near energized equipment or requiring planned outages is constrained by availability windows. | System operations or customer commitments restrict the timing and duration of available outage windows. | Construction activities dependent on outages are deferred; schedule delayed. | Construction | True |  | Renger, Andy | Active - Monitoring | Library | CN-003 | 4 | False | [6 empty] | 3 | 4 | [5 empty] | False | [15 empty] | 4
Contractor Performance Failure | 2021-2065-R-003 | URBAN SUBSTATION REBUILD | 2021-2065 | 19252 |  | Renger, Andy | 2026-03-10 | 11750 | 477 | 1 | Contractor fails to meet schedule, quality, or safety commitments, requiring intervention or replacement. | Contractor underperforms due to resource allocation, financial strain, or management failure. | Corrective action, re-bid, or contractor replacement causes significant schedule delay and cost increase. | Contract Procurement | True |  | Renger, Andy | Active - Response In Progress | Library | CP-002 | 3 | True | 235 | 587.5 | 1410 | 14.3 | 33.4 | 85.9 |  |  | Mitigate | Enforce milestone-based payment schedule and performance bond requirements. Weekly progress meetings with contractor superintendent. | Renger, Andy | 2026-06-15 | 85 | False | [15 empty] | 5
Unknown Subsurface Conditions | 2021-2065-R-004 | URBAN SUBSTATION REBUILD | 2021-2065 | 19252 |  | Renger, Andy | 2026-03-10 | 11750 | 477 | 1 | Soil, rock, groundwater, or underground utility conditions differ materially from design assumptions. | Site investigation data is insufficient or subsurface conditions vary from geotechnical baseline. | Foundation redesign, excavation rework, or schedule delay; cost increase for unanticipated conditions. | Design and Site Conditions | True |  | Renger, Andy | Active - Monitoring | Library | DS-001 | 3 | True | 176.2 | 470 | 1175 | 4.8 | 14.3 | 38.2 | [7 empty] | False | [15 empty] | 6
Land Acquisition and ROW Delays | 2020-2092-R-001 | NORTH VALLEY 69/KV SUBSTATION R | 2020-2092 | 24252 |  | Miranda, Omar | 2026-02-14 | 8000 | 454 | 1 | Acquisition of required parcels, easements, or rights-of-way takes longer than anticipated. | Property negotiations stall, owners contest acquisition, or state and federal agency parcels require extended approval. | Construction start delayed; if right-of-way is on critical path, direct schedule impact. | Real Estate/Land/Easements | True |  | Miranda, Omar | Active - Response In Progress | Library | RE-001 | 4 | True | 40 | 160 | 400 | 13.6 | 31.8 | 90.8 |  |  | Mitigate | Engaged ROW team and external land counsel. Title searches underway on two contested parcels. Weekly status with PM. | Miranda, Omar | 2026-05-30 | 120 | False | [15 empty] | 7
Permitting Delays | 2020-2092-R-002 | NORTH VALLEY 69/KV SUBSTATION R | 2020-2092 | 24252 |  | Miranda, Omar | 2026-02-14 | 8000 | 454 | 1 | Required environmental or construction permits are not issued within the anticipated timeline. | Permit applications encounter agency review delays, requests for additional information, or third-party challenges. | Construction start date delayed; if critical path activity, direct project schedule slip. | Compliance | True |  | Miranda, Omar | Active - Monitoring | Library | CO-001 | 3 | True | 40 | 120 | 240 | 9.1 | 22.7 | 54.5 | [7 empty] | False | [15 empty] | 8
Excessive Weather and Work Stoppage Days | 2020-2092-R-003 | NORTH VALLEY 69/KV SUBSTATION R | 2020-2092 | 24252 |  | Miranda, Omar | 2026-02-14 | 8000 | 454 | 1 | Adverse weather conditions cause more work stoppage days than the schedule baseline assumes. |  |  | Construction | True |  | Miranda, Omar | Active - Monitoring | Library | CN-002 | 3 | False | [13 empty] | False | [15 empty] | 9
Community Opposition to Construction Activities | 2020-2092-R-004 | NORTH VALLEY 69/KV SUBSTATION R | 2020-2092 | 24252 |  | Miranda, Omar | 2026-02-14 | 8000 | 454 | 1 | Community objections to noise, dust, traffic, or construction timing result in work restrictions or delays. | Construction operations exceed community tolerance thresholds or violate approved operating conditions. | Work hours restricted, scope of operations limited, or legal and regulatory intervention causes delay. | Stakeholders/Community | True |  | Miranda, Omar | Closed - Risk Actualized | Library | SK-001 | 4 | True | 40 | 120 | 320 | 4.5 | 13.6 | 36.3 |  |  | Mitigate | Coordinated with public affairs team; held two community meetings. Adjusted construction hours. | Miranda, Omar | 2026-04-01 | 30 | True | 2026-03-15 | 210 | 3.5 | Community complaints about noise and dust during grading phase resulted in two-week work stoppage and additional dust suppression measures costing $210k. | [11 empty] | 10
Extended Project Duration Schedule Exposure | 2015-00005-R-001 | GRANITE SUBSTATION 69KV LOOP | 2015-00005 | 17125 |  | May, Robert B | 2026-01-22 | 10250 | 721 | 1 | Long project duration (721 weeks) creates elevated exposure to permit expiration, staff turnover, and cost escalation that compounds over time. | Project initiated in 2014 with extended timeline due to phased approvals and construction sequencing. | Increased probability of regulatory re-approvals, staff changes, and material cost escalation against a fixed budget baseline. | Management and Staffing | True |  | May, Robert B | Active - Monitoring | Custom |  | 3 | False | [6 empty] | 3 | 2 | [5 empty] | False | [15 empty] | 11
Material Price Inflation | 2015-00005-R-002 | GRANITE SUBSTATION 69KV LOOP | 2015-00005 | 17125 |  | May, Robert B | 2026-01-22 | 10250 | 721 | 1 | Construction material costs (steel, copper, concrete) escalate beyond estimate assumptions. | Commodity price increases driven by market conditions, tariffs, or supply chain disruption. | Contract cost increase; potential for value engineering or scope reduction to offset. | Resources (People and Materials) | True |  | May, Robert B | Active - Response In Progress | Library | RS-003 | 3 | True | 102.5 | 307.5 | 820 | 0 | 3.6 | 10.8 |  |  | Mitigate | Early procurement of long-lead materials locked under existing contracts. Price escalation clauses reviewed with supply chain. | May, Robert B | 2026-07-01 | 50 | False | [15 empty] | 12
Key Staff Departure | 2015-00005-R-003 | GRANITE SUBSTATION 69KV LOOP | 2015-00005 | 17125 |  | May, Robert B | 2026-01-22 | 10250 | 721 | 1 | Critical project personnel (PM, lead engineer, or specialist) leave the project before completion. |  |  | Management and Staffing | True |  | May, Robert B | Active - Monitoring | Library | MS-001 | 2 | False | [13 empty] | False | [15 empty] | 13
Environmental Delays (Biological and Ecological and Cultural) | 2015-00005-R-004 | GRANITE SUBSTATION 69KV LOOP | 2015-00005 | 17125 |  | May, Robert B | 2026-01-22 | 10250 | 721 | 1 | Environmental surveys identify protected species, habitat, or cultural resources requiring mitigation or redesign. | Pre-construction surveys reveal biological, ecological, or cultural resource constraints not identified in initial assessments. | Construction window restricted or project footprint redesigned; schedule and cost impact. | Compliance | True |  | May, Robert B | Active - Monitoring | Library | CO-003 | 2 | True | 102.5 | 307.5 | 717.5 | 14.4 | 36 | 108.2 | [7 empty] | False | [15 empty] | 14
Commissioning Delays Due to Documentation Gaps | 2015-00005-R-005 | GRANITE SUBSTATION 69KV LOOP | 2015-00005 | 17125 |  | May, Robert B | 2026-01-22 | 10250 | 721 | 1 | Incomplete as-built documentation, test records, or turnover packages delay commissioning and closeout. | Contractor documentation requirements not enforced during construction; records incomplete at turnover. | Commissioning delayed pending documentation completion; project closeout extended. | Commissioning/Closeout | True |  | May, Robert B | Active - Monitoring | Library | CC-001 | 3 | False | [6 empty] | 2 | 3 | [5 empty] | False | [15 empty] | 15
Procurement Delays (Material Receiving) | 2019-0227-R-001 | Q1532 KETTLE SOLAR ONE-SANU | 2019-0227 | 21156 |  | Lewis, Dylan R (Contractor) | 2026-03-05 | 12500 | 406 | 1 | Delays in receiving procured materials disrupt construction sequencing. | Shipping, customs, or supplier production delays cause materials to arrive after required date. | Construction activities dependent on delayed materials halted or resequenced; schedule impact. | Contract Procurement | True |  | Lewis, Dylan R (Contractor) | Active - Response In Progress | Library | CP-005 | 4 | True | 37.5 | 125 | 312.5 | 4.1 | 12.2 | 32.5 |  |  | Mitigate | Expedited PO issued for inverter skids. Alternate supplier qualified as backup. Weekly delivery status from logistics team. | Lewis, Dylan R (Contractor) | 2026-05-15 | 40 | False | [15 empty] | 16
Major Equipment Delivery Delay (Transformers, Switchgear) | 2019-0227-R-002 | Q1532 KETTLE SOLAR ONE-SANU | 2019-0227 | 21156 |  | Lewis, Dylan R (Contractor) | 2026-03-05 | 12500 | 406 | 1 | Long-lead equipment not delivered within the schedule window required for construction sequencing. | Supplier production capacity constrained or logistics disruptions delay equipment delivery. | Construction sequence disrupted; critical path delayed pending equipment arrival. | Resources (People and Materials) | True |  | Lewis, Dylan R (Contractor) | Active - Monitoring | Library | RS-002 | 3 | True | 62.5 | 250 | 625 | 8.1 | 24.4 | 60.9 | [7 empty] | False | [15 empty] | 17
Factory Acceptance Test (FAT) Failure | 2019-0227-R-003 | Q1532 KETTLE SOLAR ONE-SANU | 2019-0227 | 21156 |  | Lewis, Dylan R (Contractor) | 2026-03-05 | 12500 | 406 | 1 | Major equipment (transformer, switchgear) fails factory acceptance testing, requiring remediation or replacement. | Equipment manufacturing defect identified during FAT; corrective action or remanufacture required. | Equipment delivery delayed; if long-lead item, significant schedule impact. | Quality/Safety | True |  | Lewis, Dylan R (Contractor) | Active - Monitoring | Library | QS-002 | 2 | False | [6 empty] | 3 | 4 | [5 empty] | False | [15 empty] | 18
Permitting Delays | 2019-0227-R-004 | Q1532 KETTLE SOLAR ONE-SANU | 2019-0227 | 21156 |  | Lewis, Dylan R (Contractor) | 2026-03-05 | 12500 | 406 | 1 | Required environmental or construction permits are not issued within the anticipated timeline. |  |  | Compliance | True |  | Lewis, Dylan R (Contractor) | Active - Monitoring | Library | CO-001 | 2 | False | [13 empty] | False | [15 empty] | 19
Permitting Delays | 2025-4253-R-001 | HATS WORK RELEASE 5 | 2025-4253 | 21146 |  | ODell, Jake P | 2026-04-01 | 11750 | 110 | 1 | Required environmental or construction permits are not issued within the anticipated timeline. | Permit applications encounter agency review delays, requests for additional information, or third-party challenges. | Construction start date delayed; if critical path activity, direct project schedule slip. | Compliance | True |  | ODell, Jake P | Active - Response In Progress | Library | CO-001 | 4 | True | 58.8 | 176.2 | 352.5 | 2.2 | 5.5 | 13.2 |  |  | Mitigate | Pre-application meetings scheduled with CPUC and USFS. Permit tracking log established with bi-weekly PMO review. | ODell, Jake P | 2026-06-30 | 25 | False | [15 empty] | 20
Inadequate or Inaccurate Site Information | 2025-4253-R-002 | HATS WORK RELEASE 5 | 2025-4253 | 21146 |  | ODell, Jake P | 2026-04-01 | 11750 | 110 | 1 | Surveys, soil tests, or utility records are incomplete or inaccurate, requiring additional investigation. | Pre-design site investigation is insufficient; field conditions reveal discrepancies from design basis. | Additional investigation and design revision required; construction delayed until resolution. | Design and Site Conditions | True |  | ODell, Jake P | Active - Monitoring | Library | DS-002 | 3 | True | 58.8 | 235 | 587.5 | 1.1 | 2.8 | 6.6 | [7 empty] | False | [15 empty] | 21
Land Acquisition and ROW Delays | 2025-4253-R-003 | HATS WORK RELEASE 5 | 2025-4253 | 21146 |  | ODell, Jake P | 2026-04-01 | 11750 | 110 | 1 | Acquisition of required parcels, easements, or rights-of-way takes longer than anticipated. | Property negotiations stall, owners contest acquisition, or state and federal agency parcels require extended approval. | Construction start delayed; if right-of-way is on critical path, direct schedule impact. | Real Estate/Land/Easements | True |  | ODell, Jake P | Active - Monitoring | Library | RE-001 | 3 | False | [6 empty] | 3 | 4 | [5 empty] | False | [15 empty] | 22
Permitting Delays | JR-DUMMY-1-R-001 | Reyes Dummy Project 1 | JR-DUMMY-1 | 10007 |  | Reyes, Jacob R (Contractor) | 2026-04-07 | 14000 | 48 | 1 | Required environmental or construction permits are not issued within the anticipated timeline. | Permit applications encounter agency review delays, requests for additional information, or third-party challenges. | Construction start date delayed; if critical path activity, direct project schedule slip. | Compliance | True |  | Reyes, Jacob R (Contractor) | Active - Response In Progress | Library | CO-001 | 4 | True | 70 | 210 | 420 | 1 | 2.4 | 5.8 |  |  | Mitigate | Pre-application meeting held with CPUC permitting desk. Dedicated permit coordinator assigned. Monthly tracking review with client PMO. | Reyes, Jacob R (Contractor) | 2026-06-30 | 35 | False | [15 empty] | 23
Land Acquisition and ROW Delays | JR-DUMMY-1-R-002 | Reyes Dummy Project 1 | JR-DUMMY-1 | 10007 |  | Reyes, Jacob R (Contractor) | 2026-04-07 | 14000 | 48 | 1 | Acquisition of required parcels, easements, or rights-of-way takes longer than anticipated. | Property negotiations stall, owners contest acquisition, or state and federal agency parcels require extended approval. | Construction start delayed; if right-of-way is on critical path, direct schedule impact. | Real Estate/Land/Easements | True |  | Reyes, Jacob R (Contractor) | Active - Monitoring | Library | RE-001 | 3 | True | 70 | 280 | 700 | 1.4 | 3.4 | 9.6 |  |  | Mitigate | ROW team engaged. Title searches initiated on two parcels. Escalation path to legal confirmed. | Reyes, Jacob R (Contractor) | 2026-07-15 | 60 | False | [15 empty] | 24
Scope Change After Award | JR-DUMMY-1-R-003 | Reyes Dummy Project 1 | JR-DUMMY-1 | 10007 |  | Reyes, Jacob R (Contractor) | 2026-04-07 | 14000 | 48 | 1 | Project scope is materially changed after contract award, requiring design revision and renegotiation. | Client, regulator, or contractor initiates scope change during execution phase. | Cost increase and schedule delay; change order process adds administrative burden. | Scope | True |  | Reyes, Jacob R (Contractor) | Active - Monitoring | Library | SC-001 | 3 | True | 280 | 700 | 1680 | 1 | 1.9 | 4.8 | [7 empty] | False | [15 empty] | 25
Key Staff Departure | JR-DUMMY-1-R-004 | Reyes Dummy Project 1 | JR-DUMMY-1 | 10007 |  | Reyes, Jacob R (Contractor) | 2026-04-07 | 14000 | 48 | 1 | Critical project personnel (PM, lead engineer, or specialist) leave the project before completion. |  |  | Management and Staffing | True |  | Reyes, Jacob R (Contractor) | Active - Monitoring | Library | MS-001 | 2 | False | [13 empty] | False | [15 empty] | 26
Unknown Subsurface Conditions | JR-DUMMY-2-R-001 | Reyes Dummy Project 2 | JR-DUMMY-2 | 10008 |  | Reyes, Jacob R (Contractor) | 2026-04-08 | 16000 | 48 | 1 | Soil, rock, groundwater, or underground utility conditions differ materially from design assumptions. | Site investigation data is insufficient or subsurface conditions vary from geotechnical baseline. | Foundation redesign, excavation rework, or schedule delay; cost increase for unanticipated conditions. | Design and Site Conditions | True |  | Reyes, Jacob R (Contractor) | Active - Response In Progress | Library | DS-001 | 3 | True | 240 | 640 | 1600 | 0.5 | 1.4 | 3.8 |  |  | Mitigate | Geotechnical investigation scope expanded. Third-party peer review of boring data scheduled prior to 30% design milestone. | Reyes, Jacob R (Contractor) | 2026-05-31 | 75 | False | [15 empty] | 27
Limited Contractor Competition and 4 Bid Pricing | JR-DUMMY-2-R-002 | Reyes Dummy Project 2 | JR-DUMMY-2 | 10008 |  | Reyes, Jacob R (Contractor) | 2026-04-08 | 16000 | 48 | 1 | Insufficient contractor competition results in bids materially above estimate. | Saturated contractor market reduces competitive tension; fewer qualified bidders than anticipated. | Award cost exceeds budget; reauthorization or scope reduction required. | Contract Procurement | True |  | Reyes, Jacob R (Contractor) | Active - Monitoring | Library | CP-001 | 3 | True | 320 | 800 | 1920 | 0.5 | 1 | 2.4 |  |  | Mitigate | Early market sounding conducted. Bid package structured to attract smaller qualified contractors. Evaluation criteria balanced between price and experience. | Reyes, Jacob R (Contractor) | 2026-08-01 | 0 | False | [15 empty] | 28
Labor Shortage and Labor Escalation | JR-DUMMY-2-R-003 | Reyes Dummy Project 2 | JR-DUMMY-2 | 10008 |  | Reyes, Jacob R (Contractor) | 2026-04-08 | 16000 | 48 | 1 | Insufficient skilled labor available in the market, or labor costs escalate beyond estimate. | Regional construction market demand exceeds labor supply; competing projects compete for same workforce. | Construction schedule extended due to insufficient crew size; cost increases from overtime or premium labor. | Resources (People and Materials) | True |  | Reyes, Jacob R (Contractor) | Active - Monitoring | Library | RS-001 | 3 | True | 160 | 480 | 1120 | 0.5 | 1.4 | 3.8 | [7 empty] | False | [15 empty] | 29
Political Opposition or Policy Change | JR-DUMMY-2-R-004 | Reyes Dummy Project 2 | JR-DUMMY-2 | 10008 |  | Reyes, Jacob R (Contractor) | 2026-04-08 | 16000 | 48 | 1 | Change in political environment, legislative priorities, or regulatory policy delays or suspends project approval. | State or federal political factors shift, reducing support for project authorization. | Project approval delayed, suspended, or cancelled; significant schedule and sunk-cost exposure. | Public Policy | True |  | Reyes, Jacob R (Contractor) | Active - Monitoring | Library | PP-001 | 1 | False | [6 empty] | 4 | 5 | [5 empty] | False | [15 empty] | 30
Community Opposition to Construction Activities | JR-DUMMY-2-R-005 | Reyes Dummy Project 2 | JR-DUMMY-2 | 10008 |  | Reyes, Jacob R (Contractor) | 2026-04-08 | 16000 | 48 | 1 | Community objections to noise, dust, traffic, or construction timing result in work restrictions or delays. |  |  | Stakeholders/Community | True |  | Reyes, Jacob R (Contractor) | Active - Monitoring | Library | SK-001 | 2 | False | [13 empty] | False | [15 empty] | 31
Commissioning Delays Due to Documentation Gaps | JR-DUMMY-3-R-001 | Reyes Dummy Project 3 | JR-DUMMY-3 | 10009 |  | Reyes, Jacob R (Contractor) | 2026-04-09 | 18000 | 48 | 1 | Incomplete as-built documentation, test records, or turnover packages delay commissioning and closeout. | Contractor documentation requirements not enforced during construction; records incomplete at turnover. | Commissioning delayed pending documentation completion; project closeout extended. | Commissioning/Closeout | True |  | Reyes, Jacob R (Contractor) | Closed - Risk Actualized | Library | CC-001 | 4 | True | 54 | 180 | 450 | 0.5 | 1.4 | 3.4 |  |  | Mitigate | Documentation audit conducted at 90% complete milestone. Punch list distributed to construction team. | Reyes, Jacob R (Contractor) | 2026-03-15 | 20 | True | 2026-03-15 | 145 | 2 | Incomplete as-built documentation at commissioning triggered two-week delay while records were compiled. $145k in extended field support costs incurred. | [11 empty] | 32
Factory Acceptance Test (FAT) Failure | JR-DUMMY-3-R-002 | Reyes Dummy Project 3 | JR-DUMMY-3 | 10009 |  | Reyes, Jacob R (Contractor) | 2026-04-09 | 18000 | 48 | 1 | Major equipment (transformer, switchgear) fails factory acceptance testing, requiring remediation or replacement. | Equipment manufacturing defect identified during FAT; corrective action or remanufacture required. | Equipment delivery delayed; if long-lead item, significant schedule impact. | Quality/Safety | True |  | Reyes, Jacob R (Contractor) | Closed - Risk Actualized | Library | QS-002 | 3 | True | 90 | 270 | 720 | 1 | 2.4 | 5.8 |  |  | Mitigate | FAT schedule built into contract milestones. Accenture PMO to attend FAT at factory. | Reyes, Jacob R (Contractor) | 2026-02-01 | 15 | True | 2026-03-15 | 320 | 5 | Transformer failed FAT on first attempt. Vendor required 5 weeks for rewind and re-test. $320k in costs including extended site supervision and rescheduled outage window. | [11 empty] | 33
Outage Constraints and Energized Equipment Work | JR-DUMMY-3-R-003 | Reyes Dummy Project 3 | JR-DUMMY-3 | 10009 |  | Reyes, Jacob R (Contractor) | 2026-04-09 | 18000 | 48 | 1 | Work near energized equipment or requiring planned outages is constrained by availability windows. | System operations or customer commitments restrict the timing and duration of available outage windows. | Construction activities dependent on outages are deferred; schedule delayed. | Construction | True |  | Reyes, Jacob R (Contractor) | Active - Response In Progress | Library | CN-003 | 3 | True | 90 | 360 | 900 | 1 | 2.4 | 5.8 |  |  | Mitigate | Outage window negotiated with operations 6 months in advance. Contingency outage dates reserved. | Reyes, Jacob R (Contractor) | 2026-04-15 | 0 | False | [15 empty] | 34
Inadequate PMO Oversight | JR-DUMMY-3-R-004 | Reyes Dummy Project 3 | JR-DUMMY-3 | 10009 |  | Reyes, Jacob R (Contractor) | 2026-04-09 | 18000 | 48 | 1 | Insufficient senior oversight or governance leads to undetected scope drift, quality issues, or budget overruns. | PMO staffing levels are be2 requirements or oversight cadence is insufficient for project complexity. | Deficiencies go undetected until late-stage, requiring rework and increasing cost and schedule impact. | Management and Staffing | True |  | Reyes, Jacob R (Contractor) | Active - Monitoring | Library | MS-002 | 2 | False | [6 empty] | 2 | 2 | [5 empty] | False | [15 empty] | 35
System Integration and SCADA Commissioning Failure | JR-DUMMY-3-R-005 | Reyes Dummy Project 3 | JR-DUMMY-3 | 10009 |  | Reyes, Jacob R (Contractor) | 2026-04-09 | 18000 | 48 | 1 | New asset fails to integrate with existing SCADA, protection, or control systems during commissioning. |  |  | Commissioning/Closeout | True |  | Reyes, Jacob R (Contractor) | Active - Monitoring | Library | CC-003 | 2 | False | [13 empty] | False | [15 empty] | 36
Contractor Performance Failure | JR-DUMMY-4-R-001 | Reyes Dummy Project 4 | JR-DUMMY-4 | 10010 |  | Reyes, Jacob R (Contractor) | 2026-04-10 | 20000 | 48 | 1 | Contractor fails to meet schedule, quality, or safety commitments, requiring intervention or replacement. | Contractor underperforms due to resource allocation, financial strain, or management failure. | Corrective action, re-bid, or contractor replacement causes significant schedule delay and cost increase. | Contract Procurement | True |  | Reyes, Jacob R (Contractor) | Active - Response In Progress | Library | CP-002 | 3 | True | 400 | 1000 | 2400 | 1.4 | 3.4 | 8.6 |  |  | Mitigate | Weekly contractor progress meetings established. Performance scorecard implemented with escalation trigger at two consecutive misses. Bond documents verified. | Reyes, Jacob R (Contractor) | 2026-06-01 | 0 | False | [15 empty] | 37
Utility Conflict and Underground Line Strike | JR-DUMMY-4-R-002 | Reyes Dummy Project 4 | JR-DUMMY-4 | 10010 |  | Reyes, Jacob R (Contractor) | 2026-04-10 | 20000 | 48 | 1 | Contractor strikes uncharted underground utility lines during excavation. | Existing utility record drawings are incomplete or inaccurate; potholing program insufficient. | Repair costs, work stoppage, potential injury, and schedule delay. | Construction | True |  | Reyes, Jacob R (Contractor) | Active - Response In Progress | Library | CN-001 | 3 | True | 60 | 200 | 600 | 0.2 | 0.7 | 1.9 |  |  | Mitigate | Potholing required ahead of all open-cut work. As-built utility records reviewed and reconciled with contractor survey. Emergency response protocol in place. | Reyes, Jacob R (Contractor) | 2026-05-30 | 30 | False | [15 empty] | 38
Excessive Weather and Work Stoppage Days | JR-DUMMY-4-R-003 | Reyes Dummy Project 4 | JR-DUMMY-4 | 10010 |  | Reyes, Jacob R (Contractor) | 2026-04-10 | 20000 | 48 | 1 | Adverse weather conditions cause more work stoppage days than the schedule baseline assumes. | Precipitation, wind, or temperature 5s exceed the weather contingency built into the schedule. | Schedule delayed by excess non-working days; recovery may require overtime or extended mobilization. | Construction | True |  | Reyes, Jacob R (Contractor) | Active - Monitoring | Library | CN-002 | 3 | True | 100 | 300 | 600 | 0.5 | 1.4 | 3.8 | [7 empty] | False | [15 empty] | 39
Material Price Inflation | JR-DUMMY-4-R-004 | Reyes Dummy Project 4 | JR-DUMMY-4 | 10010 |  | Reyes, Jacob R (Contractor) | 2026-04-10 | 20000 | 48 | 1 | Construction material costs (steel, copper, concrete) escalate beyond estimate assumptions. | Commodity price increases driven by market conditions, tariffs, or supply chain disruption. | Contract cost increase; potential for value engineering or scope reduction to offset. | Resources (People and Materials) | True |  | Reyes, Jacob R (Contractor) | Active - Monitoring | Library | RS-003 | 3 | True | 200 | 600 | 1600 | 0 | 0.2 | 0.7 | [7 empty] | False | [15 empty] | 40
Serious Worker Injury and Safety Incident | JR-DUMMY-4-R-005 | Reyes Dummy Project 4 | JR-DUMMY-4 | 10010 |  | Reyes, Jacob R (Contractor) | 2026-04-10 | 20000 | 48 | 1 | Serious injury or fatality causes work stoppage, regulatory investigation, and reputational impact. | Safety protocol failure or unforeseen hazard results in serious worker injury. | Construction halted during investigation; potential regulatory action and increased insurance cost. | Quality/Safety | True |  | Reyes, Jacob R (Contractor) | Active - Monitoring | Library | QS-003 | 2 | False | [6 empty] | 3 | 3 | [5 empty] | False | [15 empty] | 41
Incomplete or Inaccurate Cost Estimate | JR-DUMMY-4-R-006 | Reyes Dummy Project 4 | JR-DUMMY-4 | 10010 |  | Reyes, Jacob R (Contractor) | 2026-04-10 | 20000 | 48 | 1 | Original project cost estimate contains material errors or omissions that emerge during execution. |  |  | Scope | True |  | Reyes, Jacob R (Contractor) | Active - Monitoring | Library | SC-002 | 2 | False | [13 empty] | False | [15 empty] | 42
Regulatory Code or Standard Change | JR-DUMMY-5-R-001 | Reyes Dummy Project 5 | JR-DUMMY-5 | 10011 |  | Reyes, Jacob R (Contractor) | 2026-04-11 | 22000 | 48 | 1 | Change in applicable codes, standards, or regulations requires design revision or additional approval. | Regulatory agency issues new or amended requirements during project execution. | Design rework required; additional approval cycle adds cost and delays schedule. | Compliance | True |  | Reyes, Jacob R (Contractor) | Active - Response In Progress | Library | CO-002 | 3 | True | 220 | 550 | 1320 | 0.5 | 1.4 | 3.8 |  |  | Mitigate | Regulatory watch service engaged. Design basis document updated to reflect current code cycle. Change management process in place for mid-project amendments. | Reyes, Jacob R (Contractor) | 2026-07-31 | 20 | False | [15 empty] | 43
Hazardous Waste Discovery in ROW | JR-DUMMY-5-R-002 | Reyes Dummy Project 5 | JR-DUMMY-5 | 10011 |  | Reyes, Jacob R (Contractor) | 2026-04-11 | 22000 | 48 | 1 | Hazardous materials or contaminated soil discovered in right-of-way during acquisition or grading. | Phase II environmental assessment or ground disturbance reveals contamination requiring remediation. | Remediation required before construction can proceed; significant schedule delay and added cost. | Real Estate/Land/Easements | True |  | Reyes, Jacob R (Contractor) | Active - Monitoring | Library | RE-002 | 2 | True | 220 | 660 | 1760 | 1 | 2.4 | 7.2 |  |  | Accept | Phase I environmental assessment ordered. Phase II triggered if contamination indicators found. Budget reserve earmarked. | Reyes, Jacob R (Contractor) | 2026-08-15 | 45 | False | [15 empty] | 44
Constructability Review Failure | JR-DUMMY-5-R-003 | Reyes Dummy Project 5 | JR-DUMMY-5 | 10011 |  | Reyes, Jacob R (Contractor) | 2026-04-11 | 22000 | 48 | 1 | Construction execution methods identified in design are found to be impractical in field conditions. | Constructability review does not adequately identify field constraints; contractor identifies issues at mobilization. | Design revision and re-engineering required; construction delayed and cost increased. | Design and Site Conditions | True |  | Reyes, Jacob R (Contractor) | Active - Monitoring | Library | DS-003 | 2 | True | 220 | 660 | 1540 | 0.5 | 1.4 | 3.8 | [7 empty] | False | [15 empty] | 45
Poorly Defined Scope Driving Change Orders | JR-DUMMY-5-R-004 | Reyes Dummy Project 5 | JR-DUMMY-5 | 10011 |  | Reyes, Jacob R (Contractor) | 2026-04-11 | 22000 | 48 | 1 | Ambiguous contract scope results in disputes and change orders that increase cost. | Contract scope documents contain gaps or ambiguities that contractors exploit through change order claims. | Change order volume and cost exceed contingency; schedule impacted by dispute resolution process. | Contract Procurement | True |  | Reyes, Jacob R (Contractor) | Active - Monitoring | Library | CP-004 | 3 | False | [6 empty] | 3 | 2 | [5 empty] | False | [15 empty] | 46
Executive-Project Team Misalignment | JR-DUMMY-5-R-005 | Reyes Dummy Project 5 | JR-DUMMY-5 | 10011 |  | Reyes, Jacob R (Contractor) | 2026-04-11 | 22000 | 48 | 1 | Lack of integration between executive sponsors and project team results in misaligned decisions. |  |  | Management and Staffing | True |  | Reyes, Jacob R (Contractor) | Active - Monitoring | Library | MS-003 | 2 | False | [13 empty] | False | [15 empty] | 47
Major Equipment Delivery Delay (Transformers, Switchgear) | JR-DUMMY-5-R-006 | Reyes Dummy Project 5 | JR-DUMMY-5 | 10011 |  | Reyes, Jacob R (Contractor) | 2026-04-11 | 22000 | 48 | 1 | Long-lead equipment not delivered within the schedule window required for construction sequencing. | Supplier production capacity constrained or logistics disruptions delay equipment delivery. | Construction sequence disrupted; critical path delayed pending equipment arrival. | Resources (People and Materials) | True |  | Reyes, Jacob R (Contractor) | Active - Monitoring | Library | RS-002 | 3 | True | 110 | 440 | 1100 | 1 | 2.9 | 7.2 | [7 empty] | False | [15 empty] | 48
Hazardous Material Mitigation (Asbestos, Lead) | JR-DUMMY-5-R-007 | Reyes Dummy Project 5 | JR-DUMMY-5 | 10011 |  | Reyes, Jacob R (Contractor) | 2026-04-11 | 22000 | 48 | 1 | Hazardous materials discovered during construction require specialized mitigation before work can continue. | Demolition or site work reveals presence of asbestos, lead paint, or other hazardous materials. | Hazmat remediation required before construction can continue; cost and schedule impact. | Quality/Safety | True |  | Reyes, Jacob R (Contractor) | Active - Monitoring | Library | QS-004 | 2 | False | [6 empty] | 2 | 2 | [5 empty] | False | [15 empty] | 49
New Risk Test Submission |  | Reyes Dummy Project 1 | JR-DUMMY-1 |  |  |  | 2026-04-30 |  |  | 1 | Risk description for test submission | Technical error | Code validation. | Design and Site Conditions | True |  |  | Active — Monitoring | Custom |  | 4 | True | 1 | 15 | 200 | 2 | 3 | 6 |  |  | Mitigate | Review and edit code |  | 2026-05-05 | 0.2 | False | [5 empty] | False | [6 empty] | Major Projects |  |  | 50

## Project Metadata
Project Name | Project ID | PM Name | Project Budget ($k) | Project Duration (weeks) | Project Start Date | Project End Date | Project Phase | Project Status | Portfolio | Governance Export Date | Notes | Budget Code | ID
3 OHM SERIES REACTR ON SXPQ 230 | 2022-3181 | Markham, Chris S | 5000 | 242 | 2023-05-18 | 2028-01-12 | Construction | Active | Transmission | 2026-04-29 | Conformed dummy metadata | 24126 | 1
3 ROOTS TL6906, TL677 & TL668 | 2018-0188 | Voorhees, Todd | 5750 | 446 | 2018-08-07 | 2027-02-25 | Construction | Active | Substation | 2026-04-29 | Conformed dummy metadata | 18143 | 2
APS: HW-HG to HA-NG Upgrades | APS_HW-HG | Voorhees, Todd | 6500 | 426 | 2026-03-31 | 2034-06-01 | Planning | Active | Distribution | 2026-04-29 | Conformed dummy metadata | 10000 | 3
ARTESIAN 230KV EXPANSION-PREL | 2014-00056-ZZ | Petersen, Irina | 7250 | 482 | 2018-01-02 | 2027-03-31 | Closeout | Active | Customer | 2026-04-29 | Conformed dummy metadata | 14128 | 4
BATERIA DEL SUR PHASE II RNU | 2021-2432 | Lewis, Dylan R (Contractor) | 8000 | 244 | 2021-12-13 | 2026-08-17 | Closeout | Active | Transmission | 2026-04-29 | Conformed dummy metadata | 21156 | 5
BIG ROCK SOLAR FARM RNU | 2016-0045 | Lewis, Dylan R (Contractor) | 8750 | 248 | 2021-08-02 | 2026-05-06 | Closeout | Active | Substation | 2026-04-29 | Conformed dummy metadata | 21156 | 6
BORDER-SAN YSIDRO SUBSTATION | 2024-4111 | Miranda, Omar | 9500 | 447 | 2024-11-01 | 2033-06-01 | Planning | On Hold | Distribution | 2026-04-29 | Conformed dummy metadata | 24134 | 7
Borrego Springs 3.0 - BESS | 2021-2081 | Renger, Andy | 10250 | 354 | 2020-07-06 | 2027-04-19 | Closeout | Active | Customer | 2026-04-29 | Conformed dummy metadata | 17246 | 8
C1477: VN NEW C1477 | 2023-3513 | Voorhees, Todd | 11750 | 292 | 2021-07-26 | 2027-03-03 | Construction | Active | Substation | 2026-04-29 | Conformed dummy metadata | 20259 | 9
CALPEAK PE UNIT 1 - PTO-IF | 2022-3232 | Navi, Faraz (Contractor) | 12500 | 233 | 2023-10-18 | 2028-04-11 | Design | Active | Distribution | 2026-04-29 | Conformed dummy metadata | 21156 | 10
CAPTIVA STORAGE – SANU | 2021-2462 | Lewis, Dylan R (Contractor) | 13250 | 432 | 2020-04-15 | 2028-07-27 | Design | Active | Customer | 2026-04-29 | Conformed dummy metadata | 21156 | 11
CAST SAN LUIS REY | 2024-3904 | Voorhees, Todd | 14000 | 63 | 2025-06-30 | 2026-09-14 | Construction | Active | Transmission | 2026-04-29 | Conformed dummy metadata | 15125 | 12
CAST TALEGA | 2024-3902 | Voorhees, Todd | 14750 | 113 | 2024-07-01 | 2026-09-02 | Construction | Active | Substation | 2026-04-29 | Conformed dummy metadata | 15125 | 13
CHULA VISTA ENERGY PTO-IF | 2021-2379 | Whetstone, Jedediah W (Contractor) | 15500 | 313 | 2021-02-12 | 2027-02-17 | Closeout | Active | Distribution | 2026-04-29 | Conformed dummy metadata | 21156 | 14
CIMARRON WIND - PTO IF | 2022-3171 | Lewis, Dylan R (Contractor) | 16250 | 191 | 2023-01-10 | 2026-09-09 | Closeout | Active | Customer | 2026-04-29 | Conformed dummy metadata | 21156 | 15
CORONADO ISL. RELIABILITY REINF | 2025-4220 | Renger, Andy | 17000 | 225 | 2024-08-15 | 2028-12-08 | Design | Active | Transmission | 2026-04-29 | Conformed dummy metadata | 24136 | 16
CPEN TL690E WOOD TO STEEL | 2014-00050-ZZ | Renger, Andy | 17750 | 881 | 2013-09-15 | 2030-08-09 | Design | Active | Substation | 2026-04-29 | Conformed dummy metadata | 10143 | 17
DEL MAR NON-CAST SECURITY | 2023-3523 | Voorhees, Todd | 18500 | 345 | 2021-01-29 | 2027-09-14 | Design | Active | Distribution | 2026-04-29 | Conformed dummy metadata | 16126 | 18
DESERT JEWEL STORAGE - PTO-IF | 2025-4562 | Navi, Faraz (Contractor) | 19250 | 231 | 2025-06-26 | 2029-11-30 | Design | Active | Customer | 2026-04-29 | Conformed dummy metadata | 21156 | 19
EAST FIELD ENERGY CNTR - PTO IF | 2024-3985 | Lewis, Dylan R (Contractor) | 5000 | 336 | 2024-01-16 | 2030-06-25 | Design | On Hold | Transmission | 2026-04-29 | Conformed dummy metadata | 21156 | 20
ENCINA DECOMISSIONING 138KV | 2019-1130 | Markham, Chris S | 5750 | 356 | 2019-02-01 | 2025-12-01 | Closeout | Closed | Substation | 2026-04-29 | Conformed dummy metadata | 21145 | 21
ESCO SUB NON-CAST SECURITY | 2023-3521 | Voorhees, Todd | 6500 | 148 | 2023-08-02 | 2026-06-09 | Construction | Active | Distribution | 2026-04-29 | Conformed dummy metadata | 16126 | 22
ESCONDIDO 230KV SUB REBUILD | 2024-4134 | Petersen, Irina | 7250 | 831 | 2019-02-01 | 2035-01-10 | Planning | Active | Customer | 2026-04-29 | Conformed dummy metadata | 18127 | 23
Escondido BESS | ESCONDIDO_BESS | May, Robert B | 8000 | 370 | 2025-01-02 | 2032-02-09 | Design | Active | Transmission | 2026-04-29 | Conformed dummy metadata | 21156 | 24
FALLBROOK 2.0 | 2024-4120 | Whetstone, Jedediah W (Contractor) | 8750 | 323 | 2020-07-31 | 2026-10-13 | Closeout | Active | Substation | 2026-04-29 | Conformed dummy metadata | 21156 | 25
FALLBROOK 2.0 - SUPPORT COSTS | 2024-3756 | Markham, Chris S | 9500 | 190 | 2023-07-01 | 2027-02-25 | Construction | Active | Distribution | 2026-04-29 | Conformed dummy metadata | 21156 | 26
GRANITE SUBSTATION 69KV LOOP | 2015-00005 | May, Robert B | 10250 | 721 | 2014-02-09 | 2027-12-07 | Construction | Active | Customer | 2026-04-29 | Conformed dummy metadata | 17125 | 27
HATS WORK RELEASE 4 | 2024-3824 | ODell, Jake P | 11000 | 154 | 2023-01-05 | 2025-12-18 | Closeout | Closed | Transmission | 2026-04-29 | Conformed dummy metadata | 21146 | 28
HATS WORK RELEASE 5 | 2025-4253 | ODell, Jake P | 11750 | 110 | 2025-03-31 | 2027-05-10 | Design | Active | Substation | 2026-04-29 | Conformed dummy metadata | 21146 | 29
Helicopter Access for Transmission Structures (HATS) Work Release #3 | 2022-2623 | ODell, Jake P | 12500 | 160 | 2022-01-26 | 2025-02-24 | Closeout | Closed | Distribution | 2026-04-29 | Conformed dummy metadata | 21146 | 30
IMPERIAL BEACH NON-CAST SECURIT | 2023-3519 | Voorhees, Todd | 13250 | 154 | 2023-08-01 | 2026-07-15 | Construction | Active | Customer | 2026-04-29 | Conformed dummy metadata | 16126 | 31
Ironwood 500kV Interconnection | No P6 Project Currently | Renger, Andy | 14000 | 52 |  |  | Planning | Active | Transmission | 2026-04-29 | Conformed dummy metadata | 10001 | 32
KETTNER 69/12KV REBUILD | 2014-00599-ZZ | Markham, Chris S | 14750 | 322 | 2020-02-03 | 2026-04-09 | Closeout | Closed | Substation | 2026-04-29 | Conformed dummy metadata | 20251 | 33
KINGSLEY PHASE I RNU | 2025-4218 | Whetstone, Jedediah W (Contractor) | 15500 | 292 | 2024-11-19 | 2030-06-28 | Design | Active | Distribution | 2026-04-29 | Conformed dummy metadata | 21156 | 34
LITHIUM - CALPEAK POWER -PTO-IF | 2022-3230 | Lewis, Dylan R (Contractor) | 16250 | 162 | 2023-07-28 | 2026-09-08 | Closeout | Active | Customer | 2026-04-29 | Conformed dummy metadata | 21156 | 35
MIGUEL BK 82 | 2024-4097 | Miranda, Omar | 17750 | 403 | 2024-09-30 | 2032-06-21 | Design | Active | Substation | 2026-04-29 | Conformed dummy metadata | 24140 | 36
MIGUEL SHORT CIRCUIT MITIGATION | 2025-4352 | Miranda, Omar | 18500 | 178 | 2025-06-30 | 2028-11-30 | Design | Active | Distribution | 2026-04-29 | Conformed dummy metadata | 25143 | 37
MIGUEL-S SUNCREST 230KV LOOP-IN | 2024-3714 | Markham, Chris S | 19250 | 456 | 2021-12-10 | 2030-09-09 | Planning | Active | Customer | 2026-04-29 | Conformed dummy metadata | 23127 | 38
MISSION 69KV SUB RB | 2019-1012 | Renger, Andy | 5000 | 52 | 2012-11-13 |  | Construction | Active | Transmission | 2026-04-29 | Conformed dummy metadata | 18128 | 39
NEW DOWNTOWN 69/12KV | 2024-9876 | May, Robert B | 5750 | 520 | 2023-02-08 | 2033-01-28 | Planning | Active | Substation | 2026-04-29 | Conformed dummy metadata | 18251 | 40
NIGHTHAWK ENERGY STORAGE PTO-IF | 2021-2393 | Navi, Faraz (Contractor) | 6500 | 285 | 2021-07-01 | 2026-12-18 | Construction | Active | Distribution | 2026-04-29 | Conformed dummy metadata | 21156 | 41
NORTH JOHNSON PTO-IF | 2021-2394 | Whetstone, Jedediah W (Contractor) | 7250 | 233 | 2022-03-31 | 2026-09-22 | Closeout | Active | Customer | 2026-04-29 | Conformed dummy metadata | 21156 | 42
NORTH VALLEY 69/KV SUBSTATION R | 2020-2092 | Miranda, Omar | 8000 | 454 | 2020-06-17 | 2029-03-06 | Construction | Active | Transmission | 2026-04-29 | Conformed dummy metadata | 24252 | 43
PALA - GOMEZ CREEK BESS | 2022-2941 | Petersen, Irina | 8750 | 158 | 2022-01-11 | 2025-01-27 | Closeout | Closed | Substation | 2026-04-29 | Conformed dummy metadata | 22244 | 44
PEREGRINE PTO-IF | 2021-2091 | Lewis, Dylan R (Contractor) | 9500 | 268 | 2021-05-27 | 2026-07-21 | Closeout | Active | Distribution | 2026-04-29 | Conformed dummy metadata | 21156 | 45
PTO-IF - MT LAGUNA WIND 2 | 2018-3004 | Lewis, Dylan R (Contractor) | 10250 | 253 | 2026-04-01 | 2031-02-05 | Planning | On Hold | Customer | 2026-04-29 | Conformed dummy metadata | 21156 | 46
PURE WATER - ELE DISTRIBUTION | 2018-0165 | May, Robert B | 11000 | 410 | 2018-03-01 | 2026-01-13 | Closeout | Closed | Transmission | 2026-04-29 | Conformed dummy metadata | 18242 | 47
Q1048 Escondido Energy Center 2 | ESCONDIDO_NRG_02 | Whetstone, Jedediah W (Contractor) | 11750 | 318 | 2026-01-02 | 2032-02-10 | Planning | On Hold | Substation | 2026-04-29 | Conformed dummy metadata | 21156 | 48
Q1532 KETTLE SOLAR ONE-SANU | 2019-0227 | Lewis, Dylan R (Contractor) | 12500 | 406 | 2020-05-26 | 2028-03-09 | Construction | Active | Distribution | 2026-04-29 | Conformed dummy metadata | 21156 | 49
Q1669 POME BESS PTO-IF | 2021-2444 | Lewis, Dylan R (Contractor) | 13250 | 219 | 2022-04-08 | 2026-06-22 | Closeout | Active | Customer | 2026-04-29 | Conformed dummy metadata | 21156 | 50
Q1821 - SEGURO STORAGE - PTO-IF | 2025-4563 | Navi, Faraz (Contractor) | 14000 | 431 | 2025-08-12 | 2033-11-15 | Planning | Closed | Transmission | 2026-04-29 | Conformed dummy metadata | 21156 | 51
Q1824 - VIENTO FRONTERIZO - PTO | 2025-4564 | Lewis, Dylan R (Contractor) | 14750 | 344 | 2025-09-19 | 2032-04-23 | Planning | Active | Substation | 2026-04-29 | Conformed dummy metadata | 21156 | 52
Q2166 UMBRIEL RNU - TRANS | 2023-3247 | Lewis, Dylan R (Contractor) | 15500 | 532 | 2023-04-01 | 2033-06-13 | Design | Active | Distribution | 2026-04-29 | Conformed dummy metadata | 21156 | 53
REARRANGE TL 23013 / TL 6959 | 2020-0294 | Voorhees, Todd | 16250 | 656 | 2020-02-01 | 2032-09-02 | Design | Active | Customer | 2026-04-29 | Conformed dummy metadata | 24127 | 54
SAN MATEO SUB REBUILD - GRC | 2017-0160 | Petersen, Irina | 17000 | 776 | 2017-11-07 | 2032-09-21 | Design | On Hold | Transmission | 2026-04-29 | Conformed dummy metadata | 16261 | 55
SANDag Vesta St Bridge Crossing | SANDAG_VESTA_ST | Voorhees, Todd | 17750 | 230 | 2026-03-31 | 2030-08-30 | Planning | Active | Substation | 2026-04-29 | Conformed dummy metadata | 10002 | 56
SANDPIPER ENERGY STORAGE PTO-IF | 2021-2433 | Navi, Faraz (Contractor) | 18500 | 336 | 2021-09-27 | 2028-03-09 | Construction | Active | Distribution | 2026-04-29 | Conformed dummy metadata | 21156 | 57
SANTEE BESS - TRANSMISSION | 2023-3559 | Markham, Chris S | 19250 | 161 | 2023-09-15 | 2026-10-21 | Construction | Active | Customer | 2026-04-29 | Conformed dummy metadata | 23256 | 58
SOUTH ORANGE COUNTY REL. ENHA | 2014-00068-ZZ | Miranda, Omar | 5000 | 824 | 2011-05-02 | 2027-02-19 | Closeout | Active | Transmission | 2026-04-29 | Conformed dummy metadata | 6129 | 59
STARLIGHT SOLAR PTO-IF | 2021-2198 | Navi, Faraz (Contractor) | 5750 | 357 | 2021-05-04 | 2028-03-09 | Construction | Active | Substation | 2026-04-29 | Conformed dummy metadata | 21156 | 60
STREAMVIEW 69/12KV SUB REBUIL | 2014-00062-ZZ | Petersen, Irina | 6500 | 685 | 2017-07-21 | 2030-09-09 | Construction | Active | Distribution | 2026-04-29 | Conformed dummy metadata | 13244 | 61
SUNRISE BUTTE - PTO-IF | 2025-4219 | Navi, Faraz (Contractor) | 7250 | 172 | 2024-11-19 | 2028-03-09 | Design | Active | Customer | 2026-04-29 | Conformed dummy metadata | 21156 | 62
TL13804 WOOD TO STEEL | 2019-0255 | Markham, Chris S | 8000 | 356 | 2019-07-01 | 2026-04-28 | Closeout | Active | Transmission | 2026-04-29 | Conformed dummy metadata | 20136 | 63
TL13811 W2S | 2019-0253 | Petersen, Irina | 8750 | 381 | 2020-10-12 | 2028-02-01 | Construction | Active | Substation | 2026-04-29 | Conformed dummy metadata | 20145 | 64
TL13820 CHICARITA RECONDUCTOR | 2024-4036 | Miranda, Omar | 9500 | 321 | 2024-08-06 | 2030-10-07 | Planning | Active | Distribution | 2026-04-29 | Conformed dummy metadata | 24131 | 65
TL604 City of SD Pump Stn Reloc | TL604_SD_PUMP_STN | Voorhees, Todd | 10250 | 230 | 2026-03-31 | 2030-08-30 | Planning | Active | Customer | 2026-04-29 | Conformed dummy metadata | 10003 | 66
TL634 JUNIPER ST CRP | 2021-2096 | Voorhees, Todd | 11000 | 313 | 2021-05-06 | 2027-05-12 | Closeout | Active | Transmission | 2026-04-29 | Conformed dummy metadata | 21139 | 67
TL644 Chula Vista Bayfront Hotel | 2024-4040 | Voorhees, Todd | 11750 | 319 | 2024-08-13 | 2030-09-30 | Planning | Active | Substation | 2026-04-29 | Conformed dummy metadata | 23131 | 68
TL649 PHASE 2 WOOD TO STEEL | 2019-0268 | Miranda, Omar | 12500 | 329 | 2021-03-01 | 2027-06-22 | Closeout | Active | Distribution | 2026-04-29 | Conformed dummy metadata | 20135 | 69
TL651 BOUNDARY ST RELOCATION | 2017-0118 | Voorhees, Todd | 13250 | 358 | 2020-06-15 | 2027-04-28 | Design | Active | Customer | 2026-04-29 | Conformed dummy metadata | 21128 | 70
TL655/TL699 NCTD | TL655/TL699_NCTD | Voorhees, Todd | 14000 | 230 | 2026-01-30 | 2030-06-28 | Planning | On Hold | Transmission | 2026-04-29 | Conformed dummy metadata | 10004 | 71
TL662/666 RELIABILITY PROJECT | 2023-3558 | May, Robert B | 14750 | 189 | 2024-06-03 | 2028-01-17 | Design | Active | Substation | 2026-04-29 | Conformed dummy metadata | 18126 | 72
TL664 Sorrento to Miramar Customer Relocation | 2021-2082 | Voorhees, Todd | 15500 | 344 | 2021-03-17 | 2027-10-22 | Design | Closed | Distribution | 2026-04-29 | Conformed dummy metadata | 21129 | 73
TL664 WOOD TO STEEL | 2020-0289 | Voorhees, Todd | 16250 | 615 | 2020-05-04 | 2032-02-16 | Design | Active | Customer | 2026-04-29 | Conformed dummy metadata | 20140 | 74
TL680 EMERALD DRIVE | 2017-0129 | Voorhees, Todd | 17000 | 447 | 2017-01-03 | 2025-07-31 | Closeout | Closed | Transmission | 2026-04-29 | Conformed dummy metadata | 20130 | 75
TL680C MELROSE RECONDUCTOR | 2024-4035 | Miranda, Omar | 17750 | 341 | 2024-05-07 | 2030-11-25 | Planning | Active | Substation | 2026-04-29 | Conformed dummy metadata | 24130 | 76
TL681 BEAR VALLEY PARKWAY | 2022-3106 | Voorhees, Todd | 18500 | 266 | 2022-08-08 | 2027-09-17 | Closeout | Active | Distribution | 2026-04-29 | Conformed dummy metadata | 22127 | 77
TL683 COLE GRADE ROAD | 2016-0001-A | Voorhees, Todd | 19250 | 335 | 2020-01-26 | 2026-07-01 | Closeout | Active | Customer | 2026-04-29 | Conformed dummy metadata | 21130 | 78
TL684 HAMANN ESCONDIDO RELO | 2022-2704 | Voorhees, Todd | 5000 | 316 | 2021-12-07 | 2028-01-03 | Design | Active | Transmission | 2026-04-29 | Conformed dummy metadata | 22125 | 79
TL686-WARNERS TO NARROWS SW P | 2018-0161 | Markham, Chris S | 5750 | 1105 | 2017-05-30 | 2038-08-03 | Design | On Hold | Substation | 2026-04-29 | Conformed dummy metadata | 9142 | 80
TL6905 HDQTR PT UG RELOC | 2021-2431 | Voorhees, Todd | 6500 | 346 | 2020-12-31 | 2027-08-25 | Design | Active | Distribution | 2026-04-29 | Conformed dummy metadata | 21149 | 81
TL691 AVO-MON WOOD TO STEEL | 2014-00051-ZZ | Renger, Andy | 7250 | 647 | 2014-11-03 | 2027-03-31 | Closeout | Active | Customer | 2026-04-29 | Conformed dummy metadata | 10144 | 82
TL691 FALLBROOK | 2019-0269 | Renger, Andy | 8000 | 213 | 2026-02-23 | 2030-03-25 | Planning | Active | Transmission | 2026-04-29 | Conformed dummy metadata | 20141 | 83
TL694-WOOD TO STEEL | 2012-00014-ZZ | May, Robert B | 8750 | 671 | 2014-06-30 | 2027-05-12 | Construction | Active | Substation | 2026-04-29 | Conformed dummy metadata | 12149 | 84
TL695/6971 RECONDUCTOR & WOOD | 2014-00074-ZZ | Renger, Andy | 9500 | 943 | 2011-09-05 | 2029-10-01 | Design | Active | Distribution | 2026-04-29 | Conformed dummy metadata | 10146 | 85
TORREY PINES - NON CAST | 2021-2380 | Voorhees, Todd | 10250 | 331 | 2020-03-11 | 2026-07-21 | Construction | Active | Customer | 2026-04-29 | Conformed dummy metadata | 16126 | 86
Tule Wind Phase 2 | TULE_WIND_PH2 | Lewis, Dylan R (Contractor) | 11000 | 308 | 2026-02-27 | 2032-01-23 | Planning | On Hold | Transmission | 2026-04-29 | Conformed dummy metadata | 21156 | 87
URBAN SUBSTATION REBUILD | 2021-2065 | Renger, Andy | 11750 | 477 | 2020-02-18 | 2029-04-13 | Construction | Active | Substation | 2026-04-29 | Conformed dummy metadata | 19252 | 88
VALLEY CENTER SYS IMPROVEMENT | 2025-4354 | May, Robert B | 12500 | 282 | 2025-02-28 | 2030-07-26 | Design | Active | Distribution | 2026-04-29 | Conformed dummy metadata | 25144 | 89
VENTASSO ENERGY STORAGE - PTO | 2021-2439 | Lewis, Dylan R (Contractor) | 13250 | 187 | 2023-02-01 | 2026-09-08 | Closeout | Active | Customer | 2026-04-29 | Conformed dummy metadata | 21156 | 90
VINE SUBSTATION 230KV EXPANSION | VINE230KV | Markham, Chris S | 14000 | 510 | 2025-05-23 | 2035-03-02 | Planning | Active | Transmission | 2026-04-29 | Conformed dummy metadata | 25148 | 91
WESTSIDE CANAL BESS | 2022-2942 | Miranda, Omar | 14750 | 246 | 2021-12-29 | 2026-09-22 | Closeout | Active | Substation | 2026-04-29 | Conformed dummy metadata | 22245 | 92
Reyes Dummy Project 1 | JR-DUMMY-1 | Reyes, Jacob R (Contractor) | 14000 | 48 | 2026-01-01 | 2026-12-31 | Planning | Active | Substation | 2026-04-29 | Synthetic project – Jacob Reyes | 10007 | 93
Reyes Dummy Project 2 | JR-DUMMY-2 | Reyes, Jacob R (Contractor) | 16000 | 48 | 2026-01-01 | 2026-12-31 | Pre-Construction | Active | Customer | 2026-04-29 | Synthetic project – Jacob Reyes | 10008 | 94
Reyes Dummy Project 3 | JR-DUMMY-3 | Reyes, Jacob R (Contractor) | 18000 | 48 | 2026-01-01 | 2026-12-31 | Closeout | Active | Distribution | 2026-04-29 | Synthetic project – Jacob Reyes | 10009 | 95
Reyes Dummy Project 4 | JR-DUMMY-4 | Reyes, Jacob R (Contractor) | 20000 | 48 | 2026-01-01 | 2026-12-31 | Construction | Active | Customer | 2026-04-29 | Synthetic project – Jacob Reyes | 10010 | 96
Reyes Dummy Project 5 | JR-DUMMY-5 | Reyes, Jacob R (Contractor) | 22000 | 48 | 2026-01-01 | 2026-12-31 | Planning | Active | Substation | 2026-04-29 | Synthetic project – Jacob Reyes | 10011 | 97